TUTORIUM

Cohort management platform for tutoring centres, language schools and training institutes

Roadmap & Delivery Plan

Phased delivery, effort estimates, milestones, scope control, budget and risk

| Field | Value |
| --- | --- |
| Document ID | SL-PLN-008 |
| Version | 0.1 — draft for review |
| Date | 16 August 2026 |
| Owner | snova · github.com/snova-labs |
| Product name | Tutorium — provisional; trademark and domain clearance pending. The codebase uses no product name (see SL-ARC-002 §1), so a rename is a configuration change. |
| Status | Draft — open for edits and additions |
| Parent | SL-PRD-000 §11 (phases) · SL-SRS-001 (phase-tagged requirements) |

# Table of Contents

# 1. Approach

- Vertical slices. Each work item delivers something demonstrable end to end rather than a layer that cannot be shown.

- Phase gates, not deadlines. A phase ends when its acceptance criteria in SL-SRS-001 §7 pass, not when a date arrives. Dates below are estimates for planning, not commitments.

- Tenancy from commit one. Every table and query is tenant-scoped from the beginning; retrofitting multi-tenancy is the most expensive avoidable mistake available.

- Sell before automating. Manual onboarding through P2–P3 teaches what self-serve must do; building signup first would automate guesses.

- Cheap until it must not be. One small server carries the product through the first customers (SL-ARC-002 §11); infrastructure spend follows revenue.

# 2. Capability Mapping

Single developer (snova), working from a background in production PHP/Laravel systems, multi-tenant SaaS, relational modeling, cloud and container operations, and workflow automation.

| Capability | Level | Where it carries the plan |
| --- | --- | --- |
| PHP / Laravel — services, queues, policies, migrations | Primary strength | The entire domain layer; P1 and P2 rest on this |
| Relational modeling / MySQL | Strong | Schema, indexing, metering correctness |
| Admin panel tooling (Filament) | Strong | CRUD-heavy modules delivered in hours rather than days |
| React / Next.js | Strong | Not required until P5 portals — deliberately unused earlier |
| Docker, CI/CD, cloud operations | Working | Confined to P1 week 1 and P5 packaging, both with fallbacks |
| Payments and billing systems | Working | P3; the highest-unknown area, so estimated with the widest range |
| Workflow automation (n8n) | Working | Optional email driver only — never on the critical path |

Honest read: the academic core sits squarely in the strongest zone and is low-risk. The genuine unknowns are billing correctness (P3) and Microsoft consent flows (P5). Both are isolated behind interfaces so that difficulty there cannot contaminate the working product.

# 3. Phase Plan

Estimates assume focused full-time work by one developer and include testing and documentation. Ranges are honest, not padded — the wider the range, the less certain the work.

| Phase | Scope | Estimate | Outcome |
| --- | --- | --- | --- |
| P1 — Academic core | Tenancy foundation, identity and RBAC, org hierarchy, settings resolver, ID sequences, courses/batches/timetable/sessions, people and enrollment, attendance, dynamic grading, notes, periods, reports and delivery, dashboards, audit | 3–4 weeks | A real training centre could run on it — with manual setup |
| P2 — Tenant-ready | Presets, guided onboarding, terminology overrides, per-brand branding and email, Excel import/export, operator console with impersonation, tenant export | 1.5–2 weeks | A customer can be onboarded in 15 minutes and supported properly |
| P3 — Commercial | Plans and entitlements, metering, Stripe plus manual invoicing, trials, dunning, usage meter, legal and security artifacts | 2–3 weeks | Money can be taken from a stranger safely |
| P4 — Self-serve | Public signup, subdomains, custom domains with certificates, billing portal, in-product onboarding, marketing site | 2–3 weeks | Acquisition without a conversation |
| P5 — Distribution | On-premises packaging and licensing, Microsoft drivers (mail, Teams, calendar, SSO), learner and guardian portals | 4–6 weeks | Enterprise and channel reach |

Cumulative to first revenue (P1–P3): roughly 7–9 weeks. The earlier one-week figure belonged to a single-institute internal tool; a multi-tenant commercial product is a different undertaking, and saying so now is cheaper than discovering it in week two.

# 4. P1 Breakdown

| Week | Focus | Deliverables | Gate |
| --- | --- | --- | --- |
| W1 | Foundation | Repository, local stack, framework and panel setup, tenancy scaffolding with the isolation test harness, identity and RBAC, brands and branches, settings resolver, ID sequences | Two tenants exist; the isolation suite is green; a composed role is denied settings |
| W2 | Academic structure | Courses, batches, timetable, session generation with timezone handling, holidays, period service and reporting periods, learners, guardians, enrollments with status history | A DST-crossing batch generates correct sessions; a learner is enrolled and audited |
| W3 | Teaching workflow | Attendance policies and mobile-first grid, assessment types and grading schemes, assessments, grade grid, weighted aggregation with unit tests, teacher notes | Mixed-scheme weighted average matches a hand calculation; late-join policy verified |
| W4 | Output | Report templates and PDF rendering, storage, bulk runs with partial-failure handling, delivery tracking and retries, dashboards, audit views, hardening | Batch reports generate and deliver; a forced failure is visible and retryable |

# 5. Milestones

| Milestone | When | Go / no-go question |
| --- | --- | --- |
| M1 — Isolation proven | End W1 | Can a user of one tenant reach another’s data by any route? Must be no, with tests. |
| M2 — Structure usable | End W2 | Can a real batch and roster be entered for a real month? |
| M3 — Teachers could use it | End W3 | Would a teacher run this week’s class on it? |
| M4 — Reports out | End P1 | Did every intended recipient get a correct, branded report? |
| M5 — Onboarding works | End P2 | Can a new customer reach "attendance recorded" in 15 minutes unaided? |
| M6 — Revenue safe | End P3 | Does the invoice match a hand-counted roster, and is the paperwork in place? |
| M7 — Self-serve | End P4 | Can a stranger sign up, trial, pay and succeed with no human involvement? |

# 6. Design Partner Programme

- Recruit 3–5 centres across the three verticals during P1, ideally within travelling distance — the first customers are won by trust, not by a landing page.

- Offer: free through P2 and heavily discounted for the first year, in exchange for weekly feedback, a reference quote, and permission to use anonymized screenshots.

- Ask precisely: watch a teacher take attendance and a manager read a report, rather than collecting feature requests. Feature lists from customers describe their current workaround, not their problem.

- Cap the number deliberately. Each partner consumes support time that comes directly out of build time.

# 7. Scope Control

- The phase-tagged requirements in SL-SRS-001 are the scope. Anything untagged is not in the plan.

- A new requirement admitted mid-phase displaces something of equal size, in writing. There is no hidden slack.

- Pre-agreed de-scope order under pressure in P1: (1) trend charts on dashboards (tables remain), (2) make-up session linking, (3) note templates, (4) holiday calendars, (5) batch cloning. Attendance, grading, reporting and audit are never de-scoped — they are the product.

- Explicitly not attempted before their phase: payments, custom domains, Microsoft drivers, portals, mobile applications, fee and invoice management for tenants, AI-assisted report writing.

# 8. Risk Register

| Risk | L | I | Response |
| --- | --- | --- | --- |
| A tenancy leak reaches production | Low | Catastrophic | Automatic scoping, generated isolation tests as a blocking check, per-resource review note |
| Configurability produces an unusable setup experience | Medium | High | Presets, guided onboarding, effective-value display; activation metric watched from the first design partner |
| Metering disputes with customers | Medium | Medium | Published definition, live meter, immutable snapshots, exportable history |
| Custom grids cost more than estimated | Medium | Medium | Budgeted as bespoke pages in W3; fallback is simplified per-learner entry on the same data model |
| Compliance paperwork blocks the first EU customer | Medium | High | Artifacts listed in SL-SEC-004 §11 prepared during P3, not after a deal appears |
| Operating entity undecided at first sale | Medium | High | Manual invoicing works without card processing; decision forced at M6 |
| Solo-founder outage | Low | High | Daily deploys, documented decisions, tests as executable specification |
| Scope creep from design partners | High | Medium | Written trade rule (§7); partners see the roadmap and where their request landed |

# 9. Budget

| Stage | Infrastructure | Services | Indicative monthly |
| --- | --- | --- | --- |
| Build (P1–P2) | Local development; one small staging server | Domain, repository, error tracking free tiers | Single-digit |
| First customers (P3) | One production server plus backups | Payment processing fees; transactional email | Low double-digit |
| ~25 tenants | Larger server or split database; object storage | Email volume; monitoring | Tens |
| ~100 tenants | Split app/database/worker; managed backups | Support tooling; legal review | Low hundreds |

Infrastructure is not the constraint on this business at any realistic stage — developer time is. The correct optimization is shipping fewer, better modules, not saving money on servers.

# 10. Definition of Done

- The requirement ID is referenced in the change, and its acceptance criterion is exercised by a test.

- Authorization denial and tenant isolation are both covered for any new resource.

- Audit entries verified for new write paths; preset and seed data updated; documentation updated where behavior changed.

- Screens checked against the interface standards in SL-ARC-002 §13, including the mobile case for anything a teacher uses in class.

- Deployed to staging and demonstrated — a feature nobody has seen working is not done.

# 11. Operating Cadence After Launch

- Weekly: review activation and usage metrics, failed deliveries and error trends; one improvement shipped from customer feedback.

- Monthly: restore rehearsal, dependency updates, roadmap review against the metrics in SL-PRD-000 §9.

- Quarterly: pricing and packaging review against actual usage; security review; decision-record backlog cleared.

- Continuously: every support conversation ends with the question of what product change would have prevented it.